## Chapter Status
| First Pass |  | Kelvin Review |  | Second Pass |  | Kelvin Review |  | Final Review |  | Ready to submit | Deadlines | New Deadlines
| Who | Done | Who | Done | Who | Done | Who | Done | Who | Done | Done |  |  | Delays | Total delays
Chpater 1 | Matthew | 2021-04-03 | Kelvin | 2021-04-03 | Matthew | 2021-04-04 | Kelvin | 2021-04-05 | Jeb |  | Done | 2021-04-05 | Met
Chpater 2 | Jeb | 2021-03-29 | Kelvin | 2021-03-31 | Jeb | 2021-04-04 | Kelvin | 2021-04-04 | Matthew | 2021-04-04 | Done | 2021-04-05 | Met
Chpater 3 | Matthew | 2021-04-10 | Kelvin | 2021-04-10 | Matthew | 2021-04-11 | Kelvin |  | Jeb |  |  | 2021-04-12 | 2021-04-19 | 7 | 7
Chpater 4 | Jeb | 2021-04-10 | Kelvin |  | Jeb |  | Kelvin |  | Matthew |  |  | 2021-04-12 | 2021-04-19 |  | 7
Chpater 5 | Matthew (?) | [10 empty] | 2021-04-19 | 2021-04-26 |  | 7
Chpater 6 | Matthew: more, but straightforward changes | [10 empty] | 2021-04-26 | 2021-05-03 |  | 7
Chpater 7 | Jeb: need to explain oscillate | [10 empty] | 2021-04-26 | 2021-05-03 |  | 7
Chpater 8 | Jeb + Mattew | [10 empty] | 2021-05-03 | 2021-05-10 |  | 7
Chpater 9 | Kelvin | [10 empty] | 2021-05-24 | 2021-05-31 |  | 7
Chpater 10 | Kelvin | [10 empty] | 2021-06-07 | 2021-06-14 |  | 7
Chpater 11 | [11 empty] | 2021-06-14 | 2021-06-21 |  | 7
Chpater 12 | [11 empty] | 2021-06-21 | 2021-06-28 |  | 7
Numlist: code and text followed do not get indentation
The Done folders: DO NOT work on the file in the Done folder?]
Keep comments from the code and copy into text, update comments in code if necessary
Anything does not make sense, just put "For Kelvin" and leave as
Chapter 5 to 8: who on what?
Chapter 3: first example index.js explaination, put a comment, leave it to me.
https://www.w3.org/TR/html52/browsers.html#the-window-object
Formulas:
New Deadlines = DATE(YEAR([Deadlines]),MONTH([Deadlines]),DAY([Deadlines])+[Total delays])

## Summary
What | Chapter | Pages | Subtotal | Deliver date (after starting the project)
Intro | 1 | 15 | 15
Web GL | 2 | 30 | 45 | Week 1
Transform | 3 | 30 | 75
Mundane | 4 | 50 | 125 | Week 2 | Audio: look at: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/expandedAudio_tutorial/expandedAudio_tutorial.html
Texture | 5 | 60 | 185 | Week 3 | Refer
Behavior | 6 | 45 | 230
Camera | 7 | 35 | 265 | Week 4
Illumination | 8 | 90 | 355 | Week 5
Physics | 9 | 120 | 475 | Week 8 | Presets: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Engine/public_html/index.html
Particles | 10 | 50 | 525 | Week 10 | Stencil: look at | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/stencil_tutorial/stencil_tutorial.html
|  |  | 525 |  | Particles: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/particlesystem_tutorial/ParticleSystemTutorial.html
Background | 11 | 25 | 550 | Week 11
The Game | 12 | 25 | 575 | Week 12
575
ACK:
Remember to acknowledge the students!!
Physics material pre-sets |  | Akilas Mebrahtom
Particle system pre-sets |  | Donald Hawkins and Akilas Mebrahtom
Stencil |  | Kyla NeSmith
Audio |  | Kyla NeSmith
User Interface |  | Nicholas Carpenetti and Kyla NeSmith
Version 1 |  | Fernando Arnez
JavaScript |  | Yaniv Schwartz
Physics |  | Huaming Chen, and Michael Tanaya

## Chap1 What, who and when
Chap 1
| What | Subtasks | Who | Deadline | Next | Status
| Replace Netbeans with VSC |  | Matthew? |  | Jeb Test
|  | Screen shots (LIGHT bg, not the default dark) |  |  | Kelvin Test
Update text
re-verify extensions for: JS Lint, connetion to Chrome, glsl Syntax
Text: remember to mention ctrl-Shift-I in Chrome (include a screen shot)
| Include this diagram |  | Kelvin or Jeb
Take screen shot
1-2 paragraphs of text in intro
| Update references | at least the graphics book | Kelvin
reference to new Vector math book
Include questions and answer?
VSC Needs
| vscode live-server extension |  | https://marketplace.visualstudio.com/items?itemName=ritwickdey.LiveServer
From <https://github.com/HTML5GameEngineGroup/GTCS-GameEngine2/pull/1>
| Should install? (verify) | https://code.visualstudio.com/docs/nodejs/extensions
Live-Server extension https://marketplace.visualstudio.com/items?itemName=ritwickdey.LiveServer
READ the documentaiton! (about GoLive)
ESLint
Shader languages support for CS Code
Help: https://code.visualstudio.com/docs/languages/javascript

## Chap 2
Chap 2
| What | Subtasks | Who | Deadline
Replace all NetBeans screen shots
Re-word new project creation
update all code description
Include questions and answer?

## Chap 3
Chap 3 | Least tricky?
| What | Subtasks | Who | Deadline
Update descriptions
3.1: split core.js into: gl.js and index.js (ready for expansion and new changes)
Include questions and answer?

## Chap 4
Chap 4 | New async explanation can be tricky
| What | Subtasks | Who | Deadline
Include questions and answer?

## Chap x-template
Chap 4 | New async explanation can be tricky
| What | Subtasks | Who | Deadline
Include questions and answer?