## Chapter Status
| First Pass |  | Kelvin Review |  | Second Pass |  | Kelvin Review |  | Final Review |  | Ready to submit | Deadlines | New Deadlines
| Who | Done | Who | Done | Who | Done | Who | Done | Who | Done | Done |  |  | Delays | Total delays
Chpater 1 | Matthew | 2021-04-03 | Kelvin | 2021-04-03 | Matthew | 2021-04-04 | Kelvin | 2021-04-05 | Jeb |  | Done | 2021-04-05 | Met
Chpater 2 | Jeb | 2021-03-29 | Kelvin | 2021-03-31 | Jeb | 2021-04-04 | Kelvin | 2021-04-04 | Matthew | 2021-04-04 | Done | 2021-04-05 | Met
Chpater 3 | Matthew | 2021-04-10 | Kelvin | 2021-04-10 | Matthew | 2021-04-11 | Kelvin |  | Jeb |  | Done | 2021-04-12 | 2021-04-13 | 1 | 1
Chpater 4 | Jeb | 2021-04-10 | Kelvin |  | Jeb |  | Kelvin |  | Matthew |  |  | 2021-04-12 | 2021-04-16 | 3 | 4
Chpater 5 | Matthew (?) | [10 empty] | 2021-04-19 | 2021-04-23 |  | 4
Chpater 6 | Matthew: more, but straightforward changes | [10 empty] | 2021-04-26 | 2021-04-30 |  | 4
Chpater 7 | Jeb: need to explain oscillate | [10 empty] | 2021-04-26 | 2021-04-30 |  | 4
Chpater 8 | Jeb + Mattew | [10 empty] | 2021-05-03 | 2021-05-07 |  | 4
Chpater 9 | Kelvin | [10 empty] | 2021-05-24 | 2021-05-28 |  | 4
Chpater 10 | Kelvin | [10 empty] | 2021-06-07 | 2021-06-11 |  | 4
Chpater 11 | [11 empty] | 2021-06-14 | 2021-06-18 |  | 4
Chpater 12 | [11 empty] | 2021-06-21 | 2021-06-25 |  | 4
| Numlist: code and text followed do not get indentation | [9 empty] | SHOULD WE?
| The Done folders: DO NOT work on the file in the Done folder?] | [9 empty] | Integrate loading icon into the last final engine?
Keep comments from the code and copy into text, update comments in code if necessary
Anything does not make sense, just put "For Kelvin" and leave as
Chapter 5 to 8: who on what?
Chapter 3: first example index.js explaination, put a comment, leave it to me.
https://www.w3.org/TR/html52/browsers.html#the-window-object
Formulas:
New Deadlines = DATE(YEAR([Deadlines]),MONTH([Deadlines]),DAY([Deadlines])+[Total delays])

## Summary
What | Chapter | Pages | Subtotal | Deliver date (after starting the project)
Intro | 1 | 15 | 15
Web GL | 2 | 30 | 45 | Week 1
Transform | 3 | 30 | 75
Mundane | 4 | 50 | 125 | Week 2 | Audio: look at: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/expandedAudio_tutorial/expandedAudio_tutorial.html
Texture | 5 | 60 | 185 | Week 3 | Refer
Behavior | 6 | 45 | 230
Camera | 7 | 35 | 265 | Week 4
Illumination | 8 | 90 | 355 | Week 5
Physics | 9 | 120 | 475 | Week 8 | Presets: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Engine/public_html/index.html
Particles | 10 | 50 | 525 | Week 10 | Stencil: look at | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/stencil_tutorial/stencil_tutorial.html
|  |  | 525 |  | Particles: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/particlesystem_tutorial/ParticleSystemTutorial.html
Background | 11 | 25 | 550 | Week 11
The Game | 12 | 25 | 575 | Week 12
575
ACK:
Remember to acknowledge the students!!
Physics material pre-sets |  | Akilas Mebrahtom
Particle system pre-sets |  | Donald Hawkins and Akilas Mebrahtom
Stencil |  | Kyla NeSmith
Audio |  | Kyla NeSmith
User Interface |  | Nicholas Carpenetti and Kyla NeSmith
Version 1 |  | Fernando Arnez
JavaScript |  | Yaniv Schwartz
Physics |  | Huaming Chen, and Michael Tanaya

## Chap1 What, who and when
Chap 1
| What | Subtasks | Who | Deadline | Next | Status
| Replace Netbeans with VSC |  | Matthew? |  | Jeb Test
|  | Screen shots (LIGHT bg, not the default dark) |  |  | Kelvin Test
Update text
re-verify extensions for: JS Lint, connetion to Chrome, glsl Syntax
Text: remember to mention ctrl-Shift-I in Chrome (include a screen shot)
| Include this diagram |  | Kelvin or Jeb
Take screen shot
1-2 paragraphs of text in intro
| Update references | at least the graphics book | Kelvin
reference to new Vector math book
Include questions and answer?
VSC Needs
| vscode live-server extension |  | https://marketplace.visualstudio.com/items?itemName=ritwickdey.LiveServer
From <https://github.com/HTML5GameEngineGroup/GTCS-GameEngine2/pull/1>
| Should install? (verify) | https://code.visualstudio.com/docs/nodejs/extensions
Live-Server extension https://marketplace.visualstudio.com/items?itemName=ritwickdey.LiveServer
READ the documentaiton! (about GoLive)
ESLint
Shader languages support for CS Code
Help: https://code.visualstudio.com/docs/languages/javascript

## Chap 2
Chap 2
| What | Subtasks | Who | Deadline
Replace all NetBeans screen shots
Re-word new project creation
update all code description
Include questions and answer?

## Chap 3
Chap 3 | Least tricky?
| What | Subtasks | Who | Deadline
Update descriptions
3.1: split core.js into: gl.js and index.js (ready for expansion and new changes)
Include questions and answer?

## Chap 4
Chap 4 | New async explanation can be tricky
| What | Subtasks | Who | Deadline
Include questions and answer?

## Chap x-template
Chap 4 | New async explanation can be tricky
| What | Subtasks | Who | Deadline
Include questions and answer?