## Chapter Status
| First Pass |  | Kelvin Review |  | Second Pass |  | Kelvin Review |  | Final Review |  | Ready to submit | Deadlines | New Deadlines
| Who | Done | Who | Done | Who | Done | Who | Done | Who | Done | Done |  |  | Delays | Total delays
Chpater 1 | Matthew | 2021-04-03 | Kelvin | 2021-04-03 | Matthew | 2021-04-04 | Kelvin | 2021-04-05 | Jeb |  | Done | 2021-04-05 | Met
Chpater 2 | Jeb | 2021-03-29 | Kelvin | 2021-03-31 | Jeb | 2021-04-04 | Kelvin | 2021-04-04 | Matthew | 2021-04-04 | Done | 2021-04-05 | Met
Chpater 3 | Matthew | 2021-04-10 | Kelvin | 2021-04-10 | Matthew | 2021-04-11 | Kelvin | 2021-04-12 | Jeb | 2021-04-13 | Done | 2021-04-12 | 2021-04-13 | 1 | 1
Chpater 4 | Jeb |  | Kelvin | 2021-04-14 | Jeb | 2021-04-14 | Kelvin | 2021-04-15 | Matthew | 2021-05-15 | 2021-04-16 | 2021-04-12 | 2021-04-16 | 3 | 4
Chpater 5 | Matthew |  | Kelvin | 2021-04-23 | Matthew | 2021-04-24 | Kelvin | 2021-04-26 |  |  |  | 2021-04-19 | 2021-04-30 | 7 | 11
Chpater 6 | Matthew |  | Kelvin |  | Matthew |  | Kelvin | 2021-05-16 | Jeb |  |  | 2021-04-26 | 2021-05-18 | 11 | 22
Chpater 7 | Jeb | 2021-04-26 | Kelvin |  | Jeb | [5 empty] | 2021-05-03 | 2021-04-26 | 2021-05-03 | -15 | 7
Chpater 8 | Jeb | 2021-05-17 | Kelvin | [8 empty] | 2021-05-03 | 2021-05-10 |  | 7
Chpater 9 | Kelvin | [10 empty] | 2021-05-24 | 2021-05-31 |  | 7
Chpater 10 | Jeb | [10 empty] | 2021-06-07 | 2021-06-14 |  | 7
Chpater 11 | Matthew | 2021-05-16 | Kelvin | 2021-05-17 | Matthew | 2021-05-21 | Kelvin |  |  |  |  | 2021-06-14 | 2021-06-21 |  | 7
Chpater 12 | Jeb | [10 empty] | 2021-06-21 | 2021-06-28 |  | 7
| Numlist: code and text followed do not get indentation | [9 empty] | SHOULD WE?
| The Done folders: DO NOT work on the file in the Done folder?] | [9 empty] | Integrate loading icon into the last final engine?
Keep comments from the code and copy into text, update comments in code if necessary
Anything does not make sense, just put "For Kelvin" and leave as
https://www.w3.org/TR/html52/browsers.html#the-window-object
Formulas:
New Deadlines = DATE(YEAR([Deadlines]),MONTH([Deadlines]),DAY([Deadlines])+[Total delays])

## Final Changes Must make
Consistency
consistency needed … (with or without //, which one to use?) [Need to review Chapters 1, 2, 3, 4, 5]
| Same: | … identical to previous code .. | vs | … identical to previous projcet …
| to show: | ... implementation to follow … | vs | // new fuctinality to be define here in the next subsection |  | … more implementation details in the following steps …(Chap 5) | …
| Decide: | No comments "//" |  | This must be changed |  | this must be changed
Choose the shortest
New class: update index.js … here is the language
Lastly, remember to update the engine access file, index.js, to forward the newly defined functionality to the client.
Left-arrow
Left mouse button
Q key
Chapter 1 | debugging from VS Code extension: Debugger for Chrome
Chaper 2. | The first encounter of classes # must explain with a note, "For readability, variables will be referred to without the # symbol"
Remember to mention the "#" private syntax of JS, not adopted because of limitations, no support for subclass access, no support when source code crosses file boundary
Chapter 3 | Camera Class: Camera example (last example), take a look at the update source code and integrate (extra Enum symbol, and new simple changes)
Chapter 4: resource_map: now has reference count!
Chapter 5 | Page 15, need to explain _setShader() means "_" means only meant for local to the class
texture.js: unload must check if can actually delete
Chapter 7 | Index.js: change into one sentence "Lastly, remember to update the engine access file, index.js, to forward the newly defined functionality to the client." (introduced in Chapter 6.1)
Organize the Source Code: compare this section to Chapter 6: Organize the source code and refine.
Remove: the note on top of Page 6 (on aClass.prototype.method)
ACK:
Remember to acknowledge the students!! |  |  |  |  | Chapter 9 (Physics): should
Physics material pre-sets |  | Akilas Mebrahtom |  |  |  | Support collision: returning T/F and the colliding object … this can be a programming exercise?
Particle system pre-sets |  | Donald Hawkins and Akilas Mebrahtom
Stencil |  | Kyla NeSmith
Audio |  | Kyla NeSmith
User Interface |  | Nicholas Carpenetti and Kyla NeSmith
Version 1 |  | Fernando Arnez
JavaScript |  | Yaniv Schwartz
Physics |  | Huaming Chen, and Michael Tanaya

## Chap1 What, who and when
Chap 1
| What | Subtasks | Who | Deadline | Next | Status
| Replace Netbeans with VSC |  | Matthew? |  | Jeb Test
|  | Screen shots (LIGHT bg, not the default dark) |  |  | Kelvin Test
Update text
re-verify extensions for: JS Lint, connetion to Chrome, glsl Syntax
Text: remember to mention ctrl-Shift-I in Chrome (include a screen shot)
| Include this diagram |  | Kelvin or Jeb
Take screen shot
1-2 paragraphs of text in intro
| Update references | at least the graphics book | Kelvin
reference to new Vector math book
Include questions and answer?
VSC Needs
| vscode live-server extension |  | https://marketplace.visualstudio.com/items?itemName=ritwickdey.LiveServer
From <https://github.com/HTML5GameEngineGroup/GTCS-GameEngine2/pull/1>
| Should install? (verify) | https://code.visualstudio.com/docs/nodejs/extensions
Live-Server extension https://marketplace.visualstudio.com/items?itemName=ritwickdey.LiveServer
READ the documentaiton! (about GoLive)
ESLint
Shader languages support for CS Code
Help: https://code.visualstudio.com/docs/languages/javascript

## Chap 2
Chap 2
| What | Subtasks | Who | Deadline
Replace all NetBeans screen shots
Re-word new project creation
update all code description
Include questions and answer?

## Chap 3
Chap 3 | Least tricky?
| What | Subtasks | Who | Deadline
Update descriptions
3.1: split core.js into: gl.js and index.js (ready for expansion and new changes)
Include questions and answer?

## Chap 4
Chap 4 | New async explanation can be tricky
| What | Subtasks | Who | Deadline
Include questions and answer?

## Chap x-template
Chap 4 | New async explanation can be tricky
| What | Subtasks | Who | Deadline
Include questions and answer?

## Summary
What | Chapter | Pages | Subtotal | Deliver date (after starting the project)
Intro | 1 | 15 | 15
Web GL | 2 | 30 | 45 | Week 1
Transform | 3 | 30 | 75
Mundane | 4 | 50 | 125 | Week 2 | Audio: look at: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/expandedAudio_tutorial/expandedAudio_tutorial.html
Texture | 5 | 60 | 185 | Week 3 | Refer
Behavior | 6 | 45 | 230
Camera | 7 | 35 | 265 | Week 4
Illumination | 8 | 90 | 355 | Week 5
Physics | 9 | 120 | 475 | Week 8 | Presets: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Engine/public_html/index.html
Particles | 10 | 50 | 525 | Week 10 | Stencil: look at | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/stencil_tutorial/stencil_tutorial.html
|  |  | 525 |  | Particles: | https://gamethemedgroup.github.io/GTCS-GameEngine/V3-UI+Particles/V3-Tutorials/particlesystem_tutorial/ParticleSystemTutorial.html
Background | 11 | 25 | 550 | Week 11
The Game | 12 | 25 | 575 | Week 12
575
ACK:
Remember to acknowledge the students!!
Physics material pre-sets |  | Akilas Mebrahtom
Particle system pre-sets |  | Donald Hawkins and Akilas Mebrahtom
Stencil |  | Kyla NeSmith
Audio |  | Kyla NeSmith
User Interface |  | Nicholas Carpenetti and Kyla NeSmith
Version 1 |  | Fernando Arnez
JavaScript |  | Yaniv Schwartz
Physics |  | Huaming Chen, and Michael Tanaya